Card Copilot v3 - 6 Week Roadmap

Prepared: February 10, 2026

1) Repo Baseline (What exists now)

•	
      Auth flow exists but is prototype only: phone entry and OTP screens route users into tabs, but login state is in-memory only and OTP is not verified against a backend.

•	
      Core recommendation UI exists: Home tab supports merchant search, channel selection, recommendation card, terms modal, and route preview modal.

•	
      Recommendation logic is deterministic mock logic: output is hash based from local static card data, not personalized and not rule-engine driven.

•	
      Data is static and local: merchants and vault cards are hardcoded in source; no API sync path exists.

•	
      Vault UX is strong visually: swipeable animated card stack exists with static cards and no add-card flow wired yet.

•	
      Backlog signals in product: History tab and Settings tab are labeled "Coming Soon"; OTP "Resend" action is not wired; route sheet explicitly says "prototype preview".

•	
      Engineering constraints: Expo Router app with React Native new architecture enabled, no test scripts in package.json, and no persistence/analytics/error tracking baseline yet.

2) 6 Week Outcome Targets

Milestone M1 (Weeks 1-2): Product Foundation and Data Contracts

•	
      Finalize recommendation domain model and rule inputs (merchant, channel, amount, card, reward caps).

•	
      Add local persistence baseline for auth/session and user settings.

•	
      Replace prototype-only hardcoded defaults with typed repository layer (mock source first).

Milestone M2 (Weeks 3-4): Functional MVP Across Tabs

•	
      Ship functional History and Settings MVPs instead of placeholders.

•	
      Implement configurable spend amount and card priority to affect recommendation output.

•	
      Wire Vault add-card/edit-card flows and basic validation.

Milestone M3 (Weeks 5-6): Hardening, Metrics, and Release Readiness

•	
      Add test coverage for recommendation logic and critical navigation/auth flows.

•	
      Add analytics + crash reporting and track core activation funnel.

•	
      Complete beta release checklist for internal/preview distribution on EAS.

3) Week by Week Plan

Week

Weekly Goal

Deliverables

Key Dependencies

Primary Risks (with mitigation)

1

Stabilize architecture contracts

•	
      Define TypeScript interfaces for cards, merchants, rewards, and user preferences.

•	
      Create repository abstraction (local mock implementation first).

•	
      Document recommendation assumptions and scoring factors.

•	
      Product rules owner for reward logic.

•	
      Decision on local storage option (SecureStore or AsyncStorage).

•	
      Risk: unclear reward rules.
Mitigation: freeze v1 rule set with explicit exclusions by end of week.

2

Move from hardcoded prototype behavior to configurable core

•	
      Replace fixed amount (10000) with user controlled input + saved default.

•	
      Implement functional resend OTP UX (rate limited mock if backend is pending).

•	
      Persist auth/session state and route guard behavior across app restarts.

•	
      OTP provider decision or stub policy.

•	
      Security requirements for phone/session data.

•	
      Risk: auth flow rework causes routing regressions.
Mitigation: add smoke tests for login, logout, deep-link paths.

3

Ship History MVP

•	
      Create recommendation history event model and local storage persistence.

•	
      Render history list with merchant, card chosen, channel, savings estimate, timestamp.

•	
      Add empty, loading, and error states.

•	
      Finalized event schema from week 1.

•	
      Decision on retention window and local storage size limits.

•	
      Risk: inconsistent event writes from multiple entry points.
Mitigation: centralize write in one service method.

4

Ship Settings and Vault management MVP

•	
      Implement settings currently listed in UI: profile basics, notification prefs, default amount, card priority, privacy export trigger.

•	
      Wire vault add-card/edit metadata flow (non-sensitive fields only for v1).

•	
      Connect settings (default amount, card priority) to recommendation output.

•	
      UX copy and validation rules for settings forms.

•	
      Decision on whether real card PAN data is in scope (recommended out of scope for v1).

•	
      Risk: adding forms increases UI complexity and bugs.
Mitigation: keep scoped fields + strict input masks + QA checklist.

5

Quality, observability, and performance hardening

•	
      Add unit tests for recommendation engine and data transforms.

•	
      Add integration/smoke tests for auth gate and tab navigation.

•	
      Integrate analytics and crash reporting; define baseline dashboard.

•	
      Tooling choice for tests and analytics vendor.

•	
      Agreement on core KPIs (activation, retained usage, recommendation clickthrough).

•	
      Risk: test setup time eats feature time late in cycle.
Mitigation: prioritize critical-path tests only (auth, recommend, history write).

6

Release readiness and beta launch

•	
      Close high severity defects and polish key UX details.

•	
      Run internal beta via EAS preview/production profiles with release notes.

•	
      Deliver post-launch plan for week 7-8 based on beta telemetry and feedback.

•	
      Access to target test devices and internal testers.

•	
      Go/no-go owner for release signoff.

•	
      Risk: late cycle defects in gesture-heavy screens.
Mitigation: test vault and animations on low-end Android and iOS physical devices.

4) Explicit Dependency Register

•	
      Product: reward-rule owner to define v1 scoring policy and exclusions.

•	
      Data: source of truth for merchant categories and card reward metadata.

•	
      Auth/Security: OTP strategy (provider now vs deferred mock) and storage policy.

•	
      Tooling: test framework selection, analytics/crash SDK selection, and CI checks.

•	
      Release: internal tester pool and device matrix for Android + iOS validation.

5) Top Risks to Track Weekly

•	
      Prototype logic risk: current hash-based recommendation can produce non-trustworthy advice for real users.

•	
      Data quality risk: hardcoded merchant/card datasets can drift quickly without update workflows.

•	
      Reliability risk: no tests or error telemetry currently increases regression probability.

•	
      Scope risk: adding history, settings, vault CRUD, and auth hardening in 6 weeks is feasible only with strict v1 scope control.

•	
      Compliance risk: handling phone/card-related data needs explicit privacy boundaries before public rollout.

Definition of done at week 6: users can log in, configure key preferences, get transparent recommendations, review history, manage card metadata, and use a stable app with baseline telemetry and critical-path test coverage.